## Jira-CompleteBacklog
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project description | Priority | Resolution | Assignee | Reporter | Creator | Created | Updated | Last Viewed | Resolved | Components | Due date | Votes | Labels | Description | Environment | Watchers | Watchers | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Î£ Original Estimate | Î£ Remaining Estimate | Î£ Time Spent | Security Level | Outward issue link (Blocks) | Outward issue link (Blocks) | Outward issue link (Duplicate) | Outward issue link (Relates) | Attachment | Attachment | Custom field (Change completion date) | Custom field (Change reason) | Custom field (Change risk) | Custom field (Change start date) | Custom field (Change type) | Custom field (Code Reviewer) | Custom field (Development) | Custom field (Epic Color) | Custom field (Epic Link) | Custom field (Epic Name) | Custom field (Epic Status) | Custom field (Flagged) | Custom field (Impact) | Custom field (Issue color) | Custom field (Rank) | Custom field (Request Type) | Sprint | Sprint | Custom field (Start date) | Custom field (Story Points) | Custom field (Story point estimate) | Custom field (Tester) | Custom field ([CHART] Date of First Response) | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment
Create initial project setup | AG-19 | 10018 | Story | Done | AG | agile7 | software | admin |  | Highest | Done | admin | admin | admin | 2020-01-27 09:11 | 2020-01-31 15:40 | 2020-01-31 15:39 | 2020-01-29 11:33 |  |  | 0 |  | h2. User Story As a developer I want to have a bare bones spring boot application with a nuxt (vue) frontend. h2. Conversation Use either Maven or Gradle as build tool The build should consist of a spring boot backend and a vue frontend contained in one jar h2. Acceptance Tests As always, please try to break the application. * Application can be built on windows, linux and mac * The frontend can be started separately |  | admin | i.j.l.chow | [19 empty] | i.j.l.chow | {} |  | AG-18 | [5 empty] | 0¦i00000: |  | AG Sprint 1 |  |  | 3 |  | i.j.l.chow | 43859.4344 | 27/Jan/20 1:20 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/a86bf61b3feb42a07f4ad3529694171fb1b96fc4]: 'AG-19: Create initial project setup' | 29/Jan/20 10:25 AM;i.j.l.chow;+*Code Review*+ No bugs founds. No major issues. | 29/Jan/20 11:33 AM;i.j.l.chow;+*Functional Test*+ âœ… Runs in Windows âœ… Runs in Linux âœ… Runs in Mac âœ… Client and Server Successfully compiled
Create a procedure and location entity | AG-15 | 10014 | Story | Done | AG | agile7 | software | admin |  | Highest | Done | tccham | admin | admin | 2020-01-26 19:54 | 2020-01-31 16:11 | 2020-01-31 16:10 | 2020-01-30 17:05 |  |  | 0 |  | h2. User story As a developer I want to be able to save, update, and delete entities in the database. h2. Conversation The entities should look similar to as described below. h3. Provider ID ProviderID Name StreetAddress City State Postcode Country Latitude Longitude h3. PriceEntry ID Provider â†’ ID Procedure â†’ ID Price h3. Procedure ID ProcedureName h2. Acceptance tests The tables exist, with the structure as above. Entries can be added to the tables. Entries can be deleted from the tables. PriceEntry entries link correctly to Procedure and Provider entries. h2. Developer hint [https://spring.io/guides/gs/accessing-data-jpa/¦https://spring.io/guides/gs/accessing-data-jpa/] [https://www.baeldung.com/spring-boot-testing¦https://www.baeldung.com/spring-boot-testing] |  | admin | [9 empty] | AG-14 | AG-21 | [9 empty] | admin | {} |  | AG-13 | [5 empty] | 0¦i00006: |  | AG Sprint 1 |  |  | 3 |  | admin |  | 28/Jan/20 4:11 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/939d4bed0f93f719e54fa8d521a7d866fcfde589]: 'Merge remote-tracking branch 'origin/AG-15' into AG-15' | 30/Jan/20 1:53 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/16737e6a25ba7143b2a53b139c62030bae43f4aa]: 'AG-15 added save test' | 30/Jan/20 1:58 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/d2be34a8e9b55a2286268496d4e5451ab92ab6c3]: 'AG-15 added save test' | 30/Jan/20 2:02 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a merge request of alkajo/agile7¦https://gitlab.com/alkajo/agile7/-/merge_requests/6]: 'Resolve AG-15' | 30/Jan/20 2:09 PM;admin;cr (x) see [https://gitlab.com/alkajo/agile7/-/merge_requests/6¦https://gitlab.com/alkajo/agile7/-/merge_requests/6] | 30/Jan/20 3:52 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/c7d512f4892cbca022870e41c02c6ba36c994861]: 'AG-15: Changed int to long, format code.' | 30/Jan/20 4:09 PM;admin;cr (x) see gitlab | 30/Jan/20 4:27 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/078aa1f554d5bca3b7513d90c59a69f773b9e9cd]: 'AG-15: Reformat' | 30/Jan/20 4:27 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/b3d05614bc277fa33450132b590b4e172f6df5b9]: 'AG-15: Changed int to long, format code.' | 30/Jan/20 4:27 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/c24b84c0ed2d7a7853f92c3c92afca6e832bc288]: 'AG-15 added save test' | 30/Jan/20 4:27 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/39ff027eccd921af24654cf2d5a63fb18e3d3714]: 'AG-15 added save test' | 30/Jan/20 4:36 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/7b888fe4761d0967518149decbbf60cd801d2108]: 'AG-15: Reformat' | 30/Jan/20 4:47 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/060227c941be0d4a8fd924447315174283ccc62b]: 'AG-15: Create a procedure and location entity' | 30/Jan/20 4:47 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/941439e683b40bd2336d3be3457ad5bd2f070f97]: 'Merge branch 'AG-15' into 'master'' | 30/Jan/20 5:05 PM;admin;cr (/) â†’ see gitlab ft (/) â†’ application still builds and deploys. | 30/Jan/20 5:23 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/359a5a6b1bc328afa75c6904611b26c0407b31e7]: 'AG-15: Create a procedure and location entity' | 30/Jan/20 5:42 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/687ca8c0f8815fb43c4a9b6befb8c9fd3d11f984]: 'AG-15: Create a procedure and location entity' | 30/Jan/20 6:13 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/f0df1d702a5573c5aa545e10623d13f3aefd3e92]: 'AG-15: Create a procedure and location entity' | 30/Jan/20 6:13 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/55af675ccdab557c4c56203929a49ad8f4998d67]: 'AG-15: Create a procedure and location entity' | 30/Jan/20 6:23 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/3f5d8b08e9bdaff3ee77a39511b2f6f30b7b5b5c]: 'AG-15: Create a procedure and location entity' | 30/Jan/20 6:23 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/f1bb955a04abb25630fe0479866250c303734770]: 'AG-15: Create a procedure and location entity' | 30/Jan/20 6:45 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/a43e7270ffe6dadc2db77173555810630d092344]: 'AG-15: Create a procedure and location entity' | 30/Jan/20 6:45 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/9a08b006c801c197bfc2f8efa51a303fbd827b75]: 'AG-15: Create a procedure and location entity' | 30/Jan/20 6:45 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/1bddfd2ba783d68e3466174a1aca0790de3eb7c2]: 'AG-15: Create a procedure and location entity' | 30/Jan/20 6:45 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/4da8912b610110fc3f790d9ee2d531cae7767862]: 'AG-15: Create a procedure and location entity' | 30/Jan/20 6:50 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/17df16252042f2af0b8b912c0075d50e0769f4c5]: 'AG-15: Create a procedure and location entity' | 31/Jan/20 4:11 PM;admin;forgot to commentâ€¦ CR (/) FT (/) see gitlab merge request
Create initial website with a simple layout | AG-2 | 10001 | Story | Done | AG | agile7 | software | admin |  | Highest | Done | g.mitchell | admin | admin | 2020-01-24 21:03 | 2020-01-31 15:53 | 2020-01-31 15:43 | 2020-01-29 15:43 |  |  | 0 |  | h3. User story As a developer I want to be able to see the general layout of the website without any functionality, because this will allow multiple developers to work simultaneously on different stories in parallel. h2. Conversation It should have a top navbar with the company name It should have an empty result list to the left filling 1/3 of the width It should have a map to the right of the result list filling 2/3 of the width It should have a 100% vh. (Optional) different backgrounds for the sections h2. Acceptance Tests There are 3 visible components A full width top navigation bar exists Under the navbar a result list (1/3 width)and a container for the map (2/3 width exists) |  | admin | [9 empty] | AG-3 | AG-7 |  |  | 29/Jan/20 2:07 PM;admin;Screenshot_2020-01-29 agile7.png;https://agile7.atlassian.net/secure/attachment/10002/Screenshot_2020-01-29+agile7.png | [6 empty] | admin | {} |  | AG-1 | [5 empty] | 0¦i00003: |  | AG Sprint 1 |  |  | 2 |  | admin |  | 29/Jan/20 11:14 AM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/cbc71b5dec8404c2e147ed1a9389715ba827bda8]: 'AG-2: Initial website design' | 29/Jan/20 11:18 AM;admin;CR (x) Only one small issue. See [https://gitlab.com/alkajo/agile7/commit/cbc71b5dec8404c2e147ed1a9389715ba827bda8¦https://gitlab.com/alkajo/agile7/commit/cbc71b5dec8404c2e147ed1a9389715ba827bda8] | 29/Jan/20 11:21 AM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/2dbf8812ed38cae767b6975a17b8498cd2b763c7]: 'AG-2: Initial website design' | 29/Jan/20 11:23 AM;admin;CR LGTM (/) | 29/Jan/20 1:49 PM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/b262fdf52f0ebf05808b50939e7bffb357d98361]: 'AG-2: Initial website design' | 29/Jan/20 2:00 PM;admin;CR LGTM (/) | 29/Jan/20 2:02 PM;admin;FT (x) (/) Tests get executed (/) UI has 3 sections: Map,results, navbar (x) Not 100vh !Screenshot_2020-01-29 agile7.png¦width=1692,height=931! | 29/Jan/20 2:20 PM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/ca6dee870d5fdc067485833974cd4f43d3741d59]: 'AG-2: Initial website design' | 29/Jan/20 2:21 PM;admin;CR (/) LGTM | 29/Jan/20 2:31 PM;admin;FT (/) Retest (/) 100vh | 29/Jan/20 2:32 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a merge request of alkajo/agile7¦https://gitlab.com/alkajo/agile7/-/merge_requests/1]: 'AG-2: Initial website design' | 29/Jan/20 2:32 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/6542c2d10d55217c3b4ab7595d1ff5f4cd9ff0e5]: 'Merge branch 'AG-2' into 'master'' | 30/Jan/20 6:13 PM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/7bec37c594973e408f984e12e73f9b271c92e408]: 'AG-2: Initial website design'
Populate map with markers based on backend results | AG-34 | 10033 | Story | To Do | AG | agile7 | software | admin |  | High |  |  | admin | admin | 2020-01-30 17:33 | 2020-01-31 16:00 | 2020-01-31 16:32 |  |  |  | 0 |  | h2. User story As a customer I want to be able to see a marker containing the price of a procedure on the map h2. Conversation Add a marker containing a price to the map h2. Acceptance Tests Markers based on results should be visible on the map |  | admin | [21 empty] | {} |  | AG-1 | [5 empty] | 0¦i00062: |  | AG Sprint 2 |  |  | 3
Create a new rest endpoint to get the maximum price | AG-42 | 10041 | Story | To Do | AG | agile7 | software | admin |  | Medium |  |  | admin | admin | 2020-01-31 12:48 | 2020-01-31 16:04 | 2020-01-31 12:49 |  |  |  | 0 |  | h2. User Story As a customer the maximum price slider should be limited by the highest procedure price in the system. h2. Conversation The maximum value on the price slider should be the price of the most expensive procedure in the system h2. Acceptance Tests The maximum price the slider should go up to is of the most expensive procedure. |  | admin | [21 empty] | {} |  | AG-13 | [5 empty] | 0¦i0003j:2 |  |  |  |  | 2
Search should allow for typos | AG-41 | 10040 | Story | To Do | AG | agile7 | software | admin |  | Medium |  |  | admin | admin | 2020-01-31 12:19 | 2020-01-31 16:02 | 2020-01-31 12:36 |  |  |  | 0 |  | h2. User Story As a customer I want to be able to make simple accidental typos and still get the wanted result. h2. Conversation Must decide at which point the number of typos make the word become illegible h2. Acceptance Tests User can enter their data with limited errors and still get the expected result |  | admin | [21 empty] | {} |  | AG-13 | [5 empty] | 0¦i0004f: |  |  |  |  | 8
Ability to run UI tests and create simple automated UI test | AG-39 | 10038 | Story | To Do | AG | agile7 | software | admin |  | Medium |  |  | admin | admin | 2020-01-30 22:26 | 2020-01-31 16:39 | 2020-01-31 12:25 |  |  |  | 0 |  | h2. User Story As a developer I would like to run and create tests for the user interface for further development. h2. Conversation Add a folder that hold tests and changes made to the user interface h2. Acceptance Tests Able to test any change and edits to features into the user interface. |  | admin | [21 empty] | {} |  | AG-18 | [5 empty] | 0¦i0004e: |  |  |  |  | 8
Create rest endpoint for code and procedure autocomplete | AG-38 | 10037 | Story | To Do | AG | agile7 | software | admin |  | Medium |  |  | admin | admin | 2020-01-30 22:00 | 2020-01-31 16:17 | 2020-01-31 12:38 |  |  |  | 0 |  | h2. User Story As a customer I want to be able to have an autocomplete on the code and procedure search, thus the backend needs to provide this endpoint h2. Conversation Receives a (partial) String and should return a list of possible results h2. Acceptance Tests When searching a code it should be auto completed when partially entered When searching a procedure it should be auto completed when partially entered |  | admin | [9 empty] | AG-37 | [11 empty] | {} |  | AG-13 | [5 empty] | 0¦i0003j:a |  |  |  |  | 3
Extend search by an autocomplete for codes and procedures | AG-37 | 10036 | Story | To Do | AG | agile7 | software | admin |  | Medium |  |  | admin | admin | 2020-01-30 22:00 | 2020-01-31 16:16 | 2020-01-31 12:42 |  |  |  | 0 |  | h2. User Story As a customer I want to be able to have an autocomplete on the code and procedure search h2. Conversation Receives a (partial) String and should return a list of possible results h2. Acceptance Tests When searching a code it should be auto completed when partially entered When searching a procedure it should be auto completed when partially entered |  | admin | [21 empty] | {} |  | AG-1 | [5 empty] | 0¦i0003j:k |  |  |  |  | 3
Routing to the hospital | AG-36 | 10035 | Story | To Do | AG | agile7 | software | admin |  | Medium |  |  | admin | admin | 2020-01-30 17:36 | 2020-01-31 16:28 | 2020-01-31 12:21 |  |  |  | 0 |  | h2. User Story As a customer I want to be able to open Google Maps to route me to the hospital location. h2. Conversation Have a button for results in the list to allow users to mark and make route for users to use google maps with coordinates h2. Acceptance Test Function is able to provide link of a route between two points that is selected |  | admin | [21 empty] | {} |  | AG-1 | [5 empty] | 0¦i0004a: |  |  |  |  | 2
Create Excel export of backlog | AG-35 | 10034 | Story | To Do | AG | agile7 | software | admin |  | Medium |  |  | admin | admin | 2020-01-30 17:34 | 2020-01-31 09:03 | 2020-01-30 17:34 |  |  |  | 0 |  |  |  | admin | [21 empty] | {} |  | AG-26 | [5 empty] | 0¦i00053: |  | AG Sprint 2
Able to sort by price or distance | AG-33 | 10032 | Story | To Do | AG | agile7 | software | admin |  | Medium |  |  | admin | admin | 2020-01-30 17:32 | 2020-01-31 15:57 | 2020-01-31 11:44 |  |  |  | 0 |  | h2. User Story As a customer I want to be able to sort the results according to price or distance, thus the backend needs to provide this feature. h2. Conversation The backend should sort by price (low to high or high to low) and by distance (closest to furthest) h2. Acceptance Tests The results should be sorted by price low to high when it is requested The results should be sorted by price high to low when it is requested The results should be sorted by distance when it is requested |  | admin | [21 empty] | {} |  | AG-13 | [5 empty] | 0¦i00066: |  | AG Sprint 2 |  |  | 2
Calculate distance in the backend | AG-32 | 10031 | Story | To Do | AG | agile7 | software | admin |  | Medium |  |  | admin | admin | 2020-01-30 17:31 | 2020-01-31 16:37 | 2020-01-31 11:44 |  |  |  | 0 |  | h2. User Story As a customer I want to be able to see the distance to the hospital offering a given procedure, thus our back end needs to provide that information. h2. Conversation * Calculate the distance between the hospital providing the procedure and the users location. * The distance to the hospital is returned in miles h2. Acceptance Tests * Correct distance between user and hospital is calculated. * Distance to the hospital in miles should be visible. h2. |  | admin | [9 empty] | AG-33 | [11 empty] | {} |  | AG-13 | [5 empty] | 0¦i0005y: |  | AG Sprint 2 |  |  | 3
Update Readme in repository, add team member names | AG-31 | 10030 | Story | To Do | AG | agile7 | software | admin |  | Medium |  |  | admin | admin | 2020-01-30 14:12 | 2020-01-31 16:08 | 2020-01-31 16:41 |  |  |  | 0 |  |  |  | admin | [21 empty] | {} |  | AG-26 | [5 empty] | 0¦i00052:i |  | AG Sprint 2 | [6 empty] | 30/Jan/20 4:36 PM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/16bea20c24ace97454ba04e34dd622b48a55cd08]: 'AG-31: Edited README.md to include all members name/matric. numbers, deleted...'
Make the website mobile ready | AG-30 | 10029 | Story | To Do | AG | agile7 | software | admin |  | Medium |  |  | admin | admin | 2020-01-30 13:53 | 2020-01-31 16:00 | 2020-01-31 12:41 |  |  |  | 0 |  | h2. User Story As a customer I want to be able to use the website on a mobile device. h2. Conversation Website should be able to be formatted into a screen that has a higher vertical ratio. Would like to add a button to allow users to switch between the search menu and the map. Would be able to rotate and make the user interface look similar to the desktop app. h2. Acceptance Tests Launching website in a mobile device would look intuitive |  | admin | [21 empty] | {} |  | AG-1 | [5 empty] | 0¦i0003n: |  |  |  |  | 3
Connect the vue frontend with the backend for search | AG-29 | 10028 | Story | To Do | AG | agile7 | software | admin |  | Medium |  |  | admin | admin | 2020-01-30 13:52 | 2020-01-31 16:29 | 2020-01-31 13:34 |  |  |  | 0 |  | h2. User story As a customer I want to be able to filter the search results provided by the back end. h2. Conversation * Pass user location * Pass user selection of maximum distance from the slider component * Pass user selection of maximum price from the slider component * pass sort by selection (distance, price) h2. Acceptance Test * Correct Location data of the user is passed to the back end from the user input. * Maximum distance constraint is passed to the back end based on the slider selection. * Maximum price constraint is passed to the back end based on the slider selection. * User selection of the drop down box is passed to the back end. |  | admin | [21 empty] | {} |  | AG-1 | [5 empty] | 0¦i00054: |  | AG Sprint 2 |  |  | 3
Extend .gitignore to include build artifacts and gradle folders | AG-28 | 10027 | Bug | Done | AG | agile7 | software | admin |  | Medium | Done | admin | admin | admin | 2020-01-30 13:24 | 2020-01-31 16:07 | 2020-01-30 18:49 | 2020-01-30 14:51 |  |  | 0 |  | h2. +Bug Description+ In the CI/CD \[Ticket AG-18] some files were not ignored that should have been ignored. * Add .idea folders to the list * add gradle folders to the list * add build artifacts to the list h2. Test build and deployment should still work |  | admin | g.mitchell | [19 empty] | g.mitchell | {} |  | AG-18 | [5 empty] | 0¦i00052: |  | AG Sprint 1 |  |  |  |  | g.mitchell | 43860.6184 | 30/Jan/20 1:49 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/58475c57152faf174fe3a407b701c8145a2b724b]: 'AG-28: Remove build files and update gitignore' | 30/Jan/20 2:49 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a merge request of alkajo/agile7¦https://gitlab.com/alkajo/agile7/-/merge_requests/7]: 'AG-28: Remove build files and update gitignore' | 30/Jan/20 2:50 PM;g.mitchell;Code review done, all looks good\! | 30/Jan/20 2:50 PM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/d87ea12e72e3f6e935917449f0341fb65429f92d]: 'Merge branch 'AG-28' into 'master'' | 30/Jan/20 2:50 PM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/58475c57152faf174fe3a407b701c8145a2b724b]: 'AG-28: Remove build files and update gitignore' | 30/Jan/20 4:27 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/58475c57152faf174fe3a407b701c8145a2b724b]: 'AG-28: Remove build files and update gitignore' | 30/Jan/20 5:23 PM;admin;[sebt32¦https://gitlab.com/sebt32] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/c77e6c8d3c6526eba452cc7e3b83c02645a2c5fa]: 'AG-28: Remove build files and update gitignore' | 30/Jan/20 5:42 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/e88813e6af1639753617921ba0fd76a765b33f4c]: 'AG-28: Remove build files and update gitignore' | 30/Jan/20 6:13 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/4fc552698a14aa3bcbb1fc0bc8351186242620ca]: 'AG-28: Remove build files and update gitignore' | 30/Jan/20 6:15 PM;admin;[sebt32¦https://gitlab.com/sebt32] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/58475c57152faf174fe3a407b701c8145a2b724b]: 'AG-28: Remove build files and update gitignore' | 30/Jan/20 6:45 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/58475c57152faf174fe3a407b701c8145a2b724b]: 'AG-28: Remove build files and update gitignore'
Scrum Stand-up Meeting | AG-27 | 10026 | Task | Done | AG | agile7 | software | admin |  | Medium | Done | admin | i.j.l.chow | i.j.l.chow | 2020-01-30 11:51 | 2020-01-31 13:00 | 2020-01-30 17:23 | 2020-01-30 16:18 |  |  | 0 |  | First Recording |  | i.j.l.chow | [13 empty] | 30/Jan/20 11:51 AM;i.j.l.chow;WIN_20200130_11_26_26_Pro.mp4;https://agile7.atlassian.net/secure/attachment/10004/WIN_20200130_11_26_26_Pro.mp4 | 30/Jan/20 11:51 AM;i.j.l.chow;WIN_20200130_11_36_05_Pro.mp4;https://agile7.atlassian.net/secure/attachment/10003/WIN_20200130_11_36_05_Pro.mp4 | [6 empty] | {} |  | AG-26 | [5 empty] | 0¦i0001z: |  | AG Sprint 1
Daily Progress Meeting | AG-26 | 10025 | Epic | To Do | AG | agile7 | software | admin |  | Medium |  |  | i.j.l.chow | i.j.l.chow | 2020-01-30 11:49 | 2020-01-30 17:34 | 2020-01-31 16:41 |  |  |  | 0 |  |  |  | i.j.l.chow | [21 empty] | {} | ghx-label-7 |  | Deliverable | To Do |  |  |  | 0¦i0004m:
Create CI/CD for branch and master builds | AG-24 | 10023 | Story | Done | AG | agile7 | software | admin |  | Medium | Done | admin | admin | admin | 2020-01-27 14:37 | 2020-01-31 16:03 | 2020-01-31 15:56 | 2020-01-29 15:43 |  |  | 0 |  | h2. User Story As a developer I want to be able to track and see the latest master and branch builds. As a customer I want to have to have different environments, so that I can use production and test on staging. h2. Conversation Every branch in the repository that is pushed gets itâ€™s own environment under [https://BRANCHNAME.kahli.eu¦https://BRANCHNAME.kahli.eu] For review, production and staging an empty branch can be created from any branch and deployed under the given name. h2. Acceptance Tests * The story [https://agile7.atlassian.net/browse/AG-24¦https://agile7.atlassian.net/browse/AG-24¦smart-link] is deployed under https://ag-24.kahli.eu * Create a dummy branch built on top of ag-24 and name it 'test'. It should be built and deployed to https://test.kahli.eu |  | admin | g.mitchell | [19 empty] | g.mitchell | {} |  | AG-18 | [5 empty] | 0¦i00004: |  | AG Sprint 1 |  |  | 5 |  | g.mitchell | 43859.6524 | 28/Jan/20 1:39 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/ed76c697e3c327896a3bc7aa8160e0d42e48f063]: 'AG-24: Add CI/CD support' | 28/Jan/20 1:43 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/9195535df08318f0d52b301caff305d1423ee19d]: 'AG-24: Add CI/CD support' | 28/Jan/20 1:47 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/303f9898e01e1cd2c4f07aae78393d7a5ae0c555]: 'AG-24: Add CI/CD support' | 28/Jan/20 1:48 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/faa653867feaf2935f6b9a7e77a8d837b8bc98b0]: 'AG-24: Add CI/CD support' | 28/Jan/20 1:50 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/428c7fec69a1b0c68dfdbd346062aef1201e4f4f]: 'AG-24: Add CI/CD support' | 28/Jan/20 2:15 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/676e66bb686435916c2cfad1a031921a0c709b3b]: 'AG-24: Add CI/CD support' | 28/Jan/20 2:24 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/73bc380caa5c943abacd797fb6785fd8d627055b]: 'AG-24: Add CI/CD support' | 28/Jan/20 2:33 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/df2b45bf99f8ab5d3412954817561df19fc16aa2]: 'AG-24: Add CI/CD support' | 28/Jan/20 4:21 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/82783aa2b2eb7bd69ce6e77fce727012b6c81542]: 'AG-24: Add CI/CD support' | 29/Jan/20 2:34 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/7506c47f142697804e5d1f1c1ce4e83d0a6cac0f]: 'AG-24: Add CI/CD support' | 29/Jan/20 2:35 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a merge request of alkajo/agile7¦https://gitlab.com/alkajo/agile7/-/merge_requests/2]: 'AG-24: Add CI/CD support' | 29/Jan/20 2:37 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/374574e3bf88a8dedc1aeba6e3bad1d310c15f02]: 'AG-24: Add CI/CD support' | 29/Jan/20 2:51 PM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/82783aa2b2eb7bd69ce6e77fce727012b6c81542]: 'AG-24: Add CI/CD support' | 29/Jan/20 3:18 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/9f98c65ea3aba59f40967b7de7f5fa6dd8a9e893]: 'AG-24: Add CI/CD support' | 29/Jan/20 3:35 PM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/5460f4b88e7c238702d5918c5557bbac4aac0a35]: 'Merge branch 'AG-24' into 'master'' | 29/Jan/20 3:35 PM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/9f98c65ea3aba59f40967b7de7f5fa6dd8a9e893]: 'AG-24: Add CI/CD support' | 29/Jan/20 3:39 PM;g.mitchell;Tested AG-24 Created a new branch â€œTestâ€ Tested deployment of â€œTestâ€ branch Everything works as expected | 30/Jan/20 12:55 PM;admin;[ch6li3¦https://gitlab.com/ch6li3] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/9f98c65ea3aba59f40967b7de7f5fa6dd8a9e893]: 'AG-24: Add CI/CD support' | 30/Jan/20 4:27 PM;admin;[ElsonCTC¦https://gitlab.com/ElsonCTC] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/9f98c65ea3aba59f40967b7de7f5fa6dd8a9e893]: 'AG-24: Add CI/CD support' | 30/Jan/20 5:42 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/62855e7fa8540b542e6a691e681deb24a10533ee]: 'AG-24: Add CI/CD support' | 30/Jan/20 6:13 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/bfe19d4638579003e9e342e7f2aeb6987840907e]: 'AG-24: Add CI/CD support' | 30/Jan/20 6:15 PM;admin;[sebt32¦https://gitlab.com/sebt32] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/9f98c65ea3aba59f40967b7de7f5fa6dd8a9e893]: 'AG-24: Add CI/CD support' | 30/Jan/20 6:45 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/9f98c65ea3aba59f40967b7de7f5fa6dd8a9e893]: 'AG-24: Add CI/CD support'
Load data into database | AG-21 | 10020 | Story | In Progress | AG | agile7 | software | admin |  | Medium |  | f.pavlica | f.pavlica | f.pavlica | 2020-01-27 10:27 | 2020-01-31 16:28 | 2020-01-31 16:12 |  |  |  | 0 |  | h2. User Story As a developer, I want to load data from the csv files into the database. h2. Conversation There are 2 csv files, one with price data and one with location data (see AG-16) that should be imported. Each entry in the location data file is identifiable by the provider ID. h2. Acceptance Tests The data is loaded into the database correctly. The number of entries in the PriceEntry table matches the number of entries in the input price table. The number of entries in the Provider table matches the number of entries in the input location table, as well as the number of unique providers in the input price table. |  | admin | f.pavlica | [20 empty] | {} |  | AG-13 | [5 empty] | 0¦i00007: |  | AG Sprint 1 | AG Sprint 2 |  | 3 |  |  | 43859.5698 | 29/Jan/20 1:40 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/8eac295f1dd1db13d2bb0e9b370fa5b73b0274cb]: 'AG-21: Added MedicalDatabase controller with method to read from example csv file' | 29/Jan/20 2:03 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/9b079a612e7cdeefe9256c50e0323f4d765c9f4a]: 'AG-21: Changed MedicalDatabase to use resources folder' | 29/Jan/20 3:44 PM;admin;(flag) Flag added Flagged: cannot be merged without the entities being finished | 29/Jan/20 3:45 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/91d1e6ee2976f4367bb723a761f1df36540dcb20]: 'AG-21: Changed MedicalDatabase to use resources folder' | 29/Jan/20 3:45 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/ff678217b0d8bdc0b6109ced38d324447dbf099f]: 'AG-21: Added MedicalDatabase controller with method to read from example csv file' | 30/Jan/20 5:42 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/c3c31cbbf04822a22b899c0f8c9d3adf0a7e833c]: 'AG-21: Added MedicalDatabase controller with method to read from example csv file' | 30/Jan/20 6:13 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/ea525138aa24950c21b92afedef1897a78819ecf]: 'AG-21: Added MedicalDatabase controller with method to read from example csv file' | 30/Jan/20 6:13 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/ff120b21a70e054b3f41535d6e90d3e50d03b56b]: 'AG-21: Added MedicalDatabase controller with method to read from example csv file' | 30/Jan/20 6:45 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/73c5cd9fafee204b031bdc748e12793e392d0ec4]: 'AG-21: Added MedicalDatabase controller with method to read from example csv file' | 30/Jan/20 6:45 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/1ab09a6bb2bd85e64bd1f71c211b020084ecf6bb]: 'AG-21: Added MedicalDatabase controller with method to read from example csv file' | 30/Jan/20 6:45 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/5a585836430745266ceee541602c10b8b67127fc]: 'AG-21: Changed MedicalDatabase to use resources folder' | 30/Jan/20 6:45 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/bcff8ab995b2014e74447216f5df8dd63f9f7fd8]: 'AG-21: Added MedicalDatabase controller with method to read from example csv file' | 30/Jan/20 6:50 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/49513a99ea5722a69a7ce582a40599c57b297b31]: 'AG-21: Added MedicalDatabase controller with method to read from example csv file' | 30/Jan/20 6:50 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/80ad1fc8f89fd07b06c3d51860c62a6cc210ace0]: 'AG-21: Added MedicalDatabase controller with method to read from example csv file' | 30/Jan/20 6:50 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/c06ea7bca93321076906324214c8f013e4c8c050]: 'AG-21: Changed MedicalDatabase to use resources folder' | 30/Jan/20 7:00 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/59b4d541eb34e329172d9b60150b3f6c1ecb0a38]: 'AG-21: removed Pair dependency' | 30/Jan/20 7:02 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/fce1c638841ca0c9985254735c636caa3f3d917b]: 'AG-21: Removed Pair dependency' | 30/Jan/20 8:55 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a merge request of alkajo/agile7¦https://gitlab.com/alkajo/agile7/-/merge_requests/10]: 'Resolve AG-21' | 30/Jan/20 8:56 PM;admin;cr (x) build did not pass see [https://gitlab.com/alkajo/agile7/-/jobs/421134455¦https://gitlab.com/alkajo/agile7/-/jobs/421134455] problem with the pair import again
Search through database for data filtered by location | AG-20 | 10019 | Story | To Do | AG | agile7 | software | admin |  | Medium |  |  | f.pavlica | f.pavlica | 2020-01-27 10:16 | 2020-01-31 16:04 | 2020-01-31 12:24 |  | Backend |  | 0 |  | h1. User story As a developer, I want to get addresses within a location range from the database. h1. Conversation Functionality is out of scope A square-shaped range search will be easier than a circle-shaped one (i.e. instead of a distance from a point, use a range of acceptable lat and lng values) |  | f.pavlica | [12 empty] | AG-14 | [8 empty] | {} |  | AG-13 | [5 empty] | 0¦i0004h:
Provide infrastructre of the project and CI/CD | AG-18 | 10017 | Epic | To Do | AG | agile7 | software | admin |  | Medium |  |  | admin | admin | 2020-01-27 09:10 | 2020-01-30 22:26 | 2020-01-27 09:10 |  |  |  | 0 |  |  |  | admin | [12 empty] | AG-28 | [8 empty] | {} | ghx-label-7 |  | Infrastructure | To Do |  |  |  | 0¦i0003j:
Add missing location coordinates to provided data | AG-16 | 10015 | Story | Done | AG | agile7 | software | admin |  | Medium | Done | f.pavlica | admin | admin | 2020-01-26 19:55 | 2020-01-31 16:11 | 2020-01-31 15:40 | 2020-01-28 10:32 |  |  | 0 |  | h2. User story As a developer I need coordinates for an address in order to place it on a map. h2. Conversation For every address in the csv, there should be both lat and lng present h2. Acceptance Tests Every entry in the cvs has both lat & lng. (smoke test 20 entries) h2. Developer hint Use geocoding, either via a simple script or maybe use [https://geocode.localfocus.nl/¦https://geocode.localfocus.nl/] (or something similar) |  | admin | [9 empty] | AG-21 |  |  |  | 27/Jan/20 4:59 PM;f.pavlica;coord_addresses_MEDICARE_PROVIDER_CHARGE_INPATIENT_DRGALL_FY2017.csv;https://agile7.atlassian.net/secure/attachment/10000/coord_addresses_MEDICARE_PROVIDER_CHARGE_INPATIENT_DRGALL_FY2017.csv | [7 empty] | {} | [7 empty] | 0¦i00001: |  | AG Sprint 1 |  |  | 3 |  |  |  | 28/Jan/20 10:32 AM;admin;(/) CR: Looks good to me. Just be aware some coordinates are â€˜doubtâ€™
Create a rest endpoint for a search on code and procedure | AG-14 | 10013 | Story | In Progress | AG | agile7 | software | admin |  | Medium |  | f.pavlica | admin | admin | 2020-01-26 19:37 | 2020-01-31 16:28 | 2020-01-31 16:12 |  |  |  | 0 |  | h2. User story As a developer I want to be able to search for information about a procedure when this is requested from the frontend. h2. Conversation Define a GET rest endpoint and describe the usage in this ticket It should be possible to filter based on price and distance It should be implemented via a rest API h3. Usage {{/search?q=[query]&userlat=[user_latitude]&userlng=[user_longitude]&distance=[distance]&maxPrice[maxPrice]}} h2. Acceptance tests Searching for a procedure with filters returns a list of the PriceEntries that match the search and no others. |  | admin | [9 empty] | AG-32 | AG-33 | AG-20 | [9 empty] | {} |  | AG-13 | [5 empty] | 0¦i00007:i |  | AG Sprint 1 | AG Sprint 2 |  | 5 |  |  |  | 29/Jan/20 3:45 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/6676705598f1f8a97d7d12f057fdd6d8607c5e2c]: 'AG-14: Added search by procedure name without location or price filters,...' | 30/Jan/20 3:08 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/086db01055564185e72304923b77b8d1cc7c2c68]: 'AG-14: Added REST endpoint for search by distance and price along with the implementation' | 30/Jan/20 5:42 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/d583a72250ca74de14c199008ba3cf1d148052c2]: 'AG-14: removed commented out code' | 30/Jan/20 5:48 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a merge request of alkajo/agile7¦https://gitlab.com/alkajo/agile7/-/merge_requests/8]: 'Resolve AG-14' | 30/Jan/20 6:36 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/e9b338847a923817f5622a109f320bf27a63fb5e]: 'AG-14: removed Pair dependency' | 30/Jan/20 6:36 PM;admin;[~accountid:5e2b53f476f1a50e68c9e49c] can you add how one can call the rest endpoint and with what parameters? | 30/Jan/20 6:50 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/421584af1bbb12466670f02f367368b37a5a875f]: 'AG-14: removed Pair dependency' | 30/Jan/20 6:50 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/786ebacccf63a287756d191b824d7939c5c0b14f]: 'AG-14: removed commented out code' | 30/Jan/20 6:50 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/bc025d5ed37fc4760b428597ef3118dbbbe459d2]: 'AG-14: Added REST endpoint for search by distance and price along with the implementation' | 30/Jan/20 6:50 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/8cb1e888d08b1ae1458818e0d2c327d0f86a493a]: 'AG-14: Added search by procedure name without location or price filters,...' | 30/Jan/20 7:00 PM;admin;[FrantiÅ¡ek Pavlica¦https://gitlab.com/fpavlica] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/14cbdca0596a572dc16cfc95b03049cd37d443b4]: 'AG-14: Fixed build script to run frontend' | 30/Jan/20 8:53 PM;admin;cr (x) see gitlab
The backend that will provide the UI with rest enpoints to query information | AG-13 | 10012 | Epic | To Do | AG | agile7 | software | admin |  | Medium |  |  | admin | admin | 2020-01-25 18:17 | 2020-01-31 12:48 | 2020-01-26 15:57 |  | Backend |  | 0 |  |  |  | admin | [21 empty] | {} | ghx-label-8 |  | CW Backend | To Do |  |  |  | 0¦i0002n:
Use machine learning based on user selection | AG-11 | 10010 | Story | To Do | AG | agile7 | software | admin |  | Medium |  |  | admin | admin | 2020-01-25 18:05 | 2020-01-31 16:05 | 2020-01-31 12:03 |  |  |  | 0 | nice-to-have | h2. User story As the purchaser of the website I want it to in-cooperate machine learning to deliver more valuable results to the customers h2. Conversation Functionality is out of scope Consider using: [https://moa.cms.waikato.ac.nz/¦https://moa.cms.waikato.ac.nz/] |  | admin | [21 empty] | {} |  | AG-13 |  |  | Impediment |  |  | 0¦i0004j: | [8 empty] | 31/Jan/20 12:04 PM;admin;flagged as no one in the team has the expertise in this field
Review accessibility of the site and fix problems | AG-10 | 10009 | Story | To Do | AG | agile7 | software | admin |  | Medium |  |  | admin | admin | 2020-01-25 18:01 | 2020-01-31 16:11 | 2020-01-31 12:43 |  |  |  | 0 | nice-to-have | h2. User story As a user with disabilities I want to be able to use the website to its full potential h2. Conversation The website should be made as accessible as possible. For example the background colour on search results can be changed to soft pastel colours so itâ€™s easy on the eyes for a dyslexic user. h2. Acceptance Tests Background colour should be changed to selected colour for background. h2. Developer Hints Use [https://wave.webaim.org/¦https://wave.webaim.org/] or a similar website to test and find accessibility issues |  | admin | [21 empty] | {} |  | AG-1 | [5 empty] | 0¦i0003j:5 |  |  |  |  | 2
Add filters based on distance and price | AG-9 | 10008 | Story | Done | AG | agile7 | software | admin |  | Medium | Done | s.r.thomas | admin | admin | 2020-01-25 17:24 | 2020-01-31 16:21 | 2020-01-30 22:01 | 2020-01-30 18:35 |  |  | 0 |  | h2. User Story As a customer I want to be able to restrict the search based on price and/or distance. h2. Conversation There should be 2 sliders above the result list. Each slider should set the maximum, and not the minimum. No functionality yet, only the selected value should be â€˜savedâ€™ for both, by displaying the value near the slider (Integration with the back-end will happen in a later story). h2. Acceptance tests Users can see the two sliders. The sliders are usable (i.e. they are not just static images). The slider data is handled in a way that it can be later passed to the backend for requests. h2. Developer hints Use maybe something like this [https://buefy.org/documentation/slider¦https://buefy.org/documentation/slider] Updating the value should be â€˜lazyâ€™ [https://buefy.org/documentation/slider#lazy-update¦https://buefy.org/documentation/slider#lazy-update] |  | admin | [20 empty] | admin | {} |  | AG-1 | [5 empty] | 0¦i0001r: |  | AG Sprint 1 |  |  | 1 |  | admin |  | 30/Jan/20 12:50 PM;admin;[sebt32¦https://gitlab.com/sebt32] mentioned this issue in [a merge request of alkajo/agile7¦https://gitlab.com/alkajo/agile7/-/merge_requests/3]: 'Slider and dropdown done' | 30/Jan/20 12:59 PM;admin;cr (x) please see [https://gitlab.com/alkajo/agile7/-/merge_requests/3¦https://gitlab.com/alkajo/agile7/-/merge_requests/3] for comments | 30/Jan/20 2:53 PM;admin;[sebt32¦https://gitlab.com/sebt32] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/0ee8fb6fe75937eeb30319c519b428a518cac6b5]: 'AG-9: Slider and dropdown done' | 30/Jan/20 5:12 PM;admin;[sebt32¦https://gitlab.com/sebt32] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/44b18e25477ef3244d232ee5cc79a87fa81d71b9]: 'AG-9: Slider and dropdown done' | 30/Jan/20 5:23 PM;admin;[sebt32¦https://gitlab.com/sebt32] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/a0eef9b9336b6b82df9376dcd271c25fba7ee977]: 'AG-9: Slider Component' | 30/Jan/20 5:58 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/bae4ccda4b4e881a34203732e6141c44dd578c02]: 'AG-9: Slider Component' | 30/Jan/20 5:58 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/fc54a0fd2fbee73bb0786b2ad1e607b88feb7752]: 'AG-9: Slider and dropdown done' | 30/Jan/20 5:58 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/ff499d239378c701717915958f0a7f55bb392013]: 'AG-9: Slider and dropdown done' | 30/Jan/20 6:15 PM;admin;[sebt32¦https://gitlab.com/sebt32] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/84dc9fe2f9034b09b6cfe4867b0227eb74505dfc]: 'AG-9: Dropdown Component' | 30/Jan/20 6:16 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/f6469799023e42526059575dd59d155a64742a89]: 'AG-9: Slider Component' | 30/Jan/20 6:18 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a merge request of alkajo/agile7¦https://gitlab.com/alkajo/agile7/-/merge_requests/9]: 'WIP: Resolve AG-9' | 30/Jan/20 6:34 PM;admin;[sebt32¦https://gitlab.com/sebt32] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/e20e52a99300e1515a3bc572f4083a49257b8786]: 'AG-9: Slider Component' | 30/Jan/20 6:34 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/9da05db3e5b3989ef6735595d13545b403d18fa5]: 'Merge branch 'AG-9' into 'master'' | 30/Jan/20 6:35 PM;admin;cr (/) see gitlab ft (/) see gitlab | 30/Jan/20 6:55 PM;admin;[sebt32¦https://gitlab.com/sebt32] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/5e74fea47e4591ec419ed8da1161a843373dfa25]: 'AG-9: Dropdown Component'
Ability to order results by price or distance | AG-8 | 10007 | Story | Resolved | AG | agile7 | software | admin |  | Medium |  | s.r.thomas | admin | admin | 2020-01-25 17:19 | 2020-01-31 16:28 | 2020-01-31 11:14 |  |  |  | 0 |  | h2. User Story As a customer I want to be able to sort the price and distance of the results. h2. Conversations Add sorting buttons for both price (indicating both up and down) Actual sorting will be done on the back end, thus the sort order (price and distance) will be in a later story appended to the query. h2. Acceptance Test * Displays a drop down box with a choice of sorting by Ascending price, descending price and ascending distance. * Text in box changes to the relevant selection when chosen. |  | admin | [21 empty] | {} |  | AG-1 | [5 empty] | 0¦i00027: |  | AG Sprint 1 | AG Sprint 2 |  | 1 |  |  |  | 30/Jan/20 6:11 PM;admin;[sebt32¦https://gitlab.com/sebt32] mentioned this issue in [a merge request of alkajo/agile7¦https://gitlab.com/alkajo/agile7/-/merge_requests/9]: 'WIP: Resolve AG-8' | 30/Jan/20 6:20 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a merge request of alkajo/agile7¦https://gitlab.com/alkajo/agile7/-/merge_requests/9]: 'WIP: Resolve AG-8' | 31/Jan/20 8:36 AM;admin;[sebt32¦https://gitlab.com/sebt32] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/2c97996f54ffeec2c58a33936ca947f59ec6477d]: 'AG-8: Dropdown Component Tests Passed' | 31/Jan/20 12:13 PM;admin;[sebt32¦https://gitlab.com/sebt32] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/f5a14947f8be40c6002c137eaf9fc4493d5b1709]: 'AG-8: Dropdown Component'
Component displaying information with details | AG-7 | 10006 | Story | Done | AG | agile7 | software | admin |  | Medium | Done | i.j.l.chow | admin | admin | 2020-01-25 17:06 | 2020-01-31 15:55 | 2020-01-31 15:53 | 2020-01-30 17:16 |  |  | 0 |  | h2. User Story As a developer I want to be to have a reusable vue component displaying a single search result. h2. Conversation Create a vue component that displays one result in the result component. A component should be reusable for all results in the list. A single static component should be displayed in the result list, as an outcome of this story. It should contain price, hospital name and procedure name h2. Acceptance Tests A vue component exists that displays: * hospital name * price in USD * distance in miles h2. Developer Hint [https://vuejs.org/v2/guide/components.html¦https://vuejs.org/v2/guide/components.html] |  | admin | [9 empty] | AG-3 | [10 empty] | admin | {} |  | AG-1 | [5 empty] | 0¦i00003:i |  | AG Sprint 1 |  |  | 2 |  |  |  | 30/Jan/20 7:23 AM;admin;[ch6li3¦https://gitlab.com/ch6li3] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/9e5ae29ce895d295809c5a661cfa0bd0f454add6]: 'AG-7' | 30/Jan/20 12:52 PM;admin;[ch6li3¦https://gitlab.com/ch6li3] mentioned this issue in [a merge request of alkajo/agile7¦https://gitlab.com/alkajo/agile7/-/merge_requests/5]: 'AG-7' | 30/Jan/20 12:55 PM;admin;[ch6li3¦https://gitlab.com/ch6li3] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/89d86d356618046a357087c3d94370653d87f13c]: 'AG-7' | 30/Jan/20 1:14 PM;admin;cr (x) see [https://gitlab.com/alkajo/agile7/-/merge_requests/5/diffs#d5df275d37989f25cf9ee63e66cfe30683a9a0fb_0_36¦https://gitlab.com/alkajo/agile7/-/merge_requests/5/diffs#d5df275d37989f25cf9ee63e66cfe30683a9a0fb_0_36] only small things | 30/Jan/20 1:30 PM;admin;[ch6li3¦https://gitlab.com/ch6li3] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/b312f46ccdd1ab90279c610819c4d10dc20c657a]: 'AG-7: Procedure Component' | 30/Jan/20 3:33 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/c5830ec487fbdb606baaf396e098247c019d0c23]: 'AG-7: Procedure Component' | 30/Jan/20 4:04 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/5762f7e7a3a4bf5ede595c832fd66750e12aff9f]: 'AG-7: Procedure Component' | 30/Jan/20 4:57 PM;admin;[ch6li3¦https://gitlab.com/ch6li3] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/c8c245c94d960788c9d84357dd0a6932b033229c]: 'AG-7: Procedure Component' | 30/Jan/20 5:03 PM;admin;[ch6li3¦https://gitlab.com/ch6li3] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/cbcbdf679e3fd1a4627b8dd84f41f31eb0283101]: 'AG-7: Procedure Component' | 30/Jan/20 5:03 PM;admin;[ch6li3¦https://gitlab.com/ch6li3] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/02f4e39dc0b65e1f6f702099918a63fdd927fb9c]: 'AG-7: Procedure Component' | 30/Jan/20 5:15 PM;admin;[ch6li3¦https://gitlab.com/ch6li3] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/4493c453751bb9ccd9085b4e6d4f2704c53fc410]: 'AG-7: Procedure Component' | 30/Jan/20 5:16 PM;admin;cr (/) see [https://gitlab.com/alkajo/agile7/-/merge_requests/5¦https://gitlab.com/alkajo/agile7/-/merge_requests/5] ft (/) I can see 3 static result components | 30/Jan/20 5:58 PM;admin;[Johannes K¦https://gitlab.com/alkajo] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/e4a0d7d261fd6621044c379bcdafcba52960d054]: 'Merge branch 'AG-7' into 'master'' | 30/Jan/20 6:13 PM;admin;[ch6li3¦https://gitlab.com/ch6li3] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/e6423f2d82a0e2a213a726a8dec8267bddb5c893]: 'AG-7: Procedure Component'
Integrate OSM maps | AG-5 | 10004 | Story | Done | AG | agile7 | software | admin |  | Medium | Done | g.mitchell | admin | admin | 2020-01-24 21:28 | 2020-01-31 16:08 | 2020-01-31 16:12 | 2020-01-30 13:19 |  |  | 0 |  | h2. User Story As a user I want to be able to see a map next to the search results h2. Conversation The map should be implemented using OpenStreetMaps h2. Acceptance tests * A map is displayed in the right â€˜mapâ€™ section * The map is usable - the user can move the map viewport around and see it change correctly h2. Developer hints Maybe use [https://github.com/schlunsen/nuxt-leaflet¦https://github.com/schlunsen/nuxt-leaflet¦smart-link] h2. |  | admin | i.j.l.chow | [8 empty] | AG-4 | [10 empty] | i.j.l.chow | {} |  | AG-1 | [5 empty] | 0¦i00008: |  | AG Sprint 1 |  |  | 2 |  | i.j.l.chow | 43860.5559 | 29/Jan/20 4:16 PM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/ef59917e170837194fc68950d6ae419808eaccf1]: 'AG-5: Implemented OSM Map and changed standard coordinates to Washington D.C' | 29/Jan/20 4:19 PM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/76e62881c430205d8fc94e544d17dc914d9f8642]: 'AG-5: Implemented OSM Map and changed standard coordinates to Washington D.C' | 29/Jan/20 4:25 PM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/c19d5c38d784af1a540621daa109318f5f417447]: 'AG-5: Implemented OSM Map and changed standard coordinates to Washington D.C' | 29/Jan/20 4:46 PM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/51b47ff82318be4745500915617752d3644c7265]: 'AG-5: Implemented OSM Map and changed standard coordinates to Washington D.C' | 30/Jan/20 12:51 PM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a merge request of alkajo/agile7¦https://gitlab.com/alkajo/agile7/-/merge_requests/4]: 'AG-5: Implemented OSM Map and changed standard coordinates to Washington D.C' | 30/Jan/20 1:18 PM;admin;[ch6li3¦https://gitlab.com/ch6li3] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/2a547b7e706a7bd2c1f6dc856845ed7aed051e2d]: 'Merge branch 'AG-5' into 'master'' | 30/Jan/20 1:20 PM;i.j.l.chow;+*Code Review*+ No bugs founds. No major issues. +*Functional Test*+ âœ… Apps runs smoothly âœ… Able to pan around the map âœ… Able to zoom with buttons and scroll on mouse | 30/Jan/20 5:42 PM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/3d9341eea09705bb36823cab64ab0b9612c8acf7]: 'AG-5: Implemented OSM Map and changed standard coordinates to Washington D.C' | 30/Jan/20 6:13 PM;admin;[gmitchell2000¦https://gitlab.com/gmitchell2000] mentioned this issue in [a commit of alkajo/agile7¦https://gitlab.com/alkajo/agile7/commit/b9f4363f94e426071f69c308a2a92200936a2690]: 'AG-5: Implemented OSM Map and changed standard coordinates to Washington D.C'
Search based on procedures and code | AG-3 | 10002 | Story | In Progress | AG | agile7 | software | admin |  | Medium |  | i.j.l.chow | admin | admin | 2020-01-24 21:06 | 2020-01-31 16:28 | 2020-01-31 16:03 |  |  |  | 0 |  | h3. User story As a customer I want to have a search box in the navigation bar that allows one to search by procedure name or by procedure code. h2. Conversation Add a text input to the navigation bar The placeholder text should be 'Search for procedures or by code' Once searched, it should display dummy data of 10 entries in the result list. h2. Acceptance Tests Before searching the result list is empty After searching 10 dummy results are visible h2. Technical Hint Start with an empty â€˜result arrayâ€™ in the vue backend, once clicked add dummy results. Iterate over the result array |  | admin | [21 empty] | {} |  | AG-1 | [5 empty] | 0¦i00004:i |  | AG Sprint 1 | AG Sprint 2 |  | 3
CW Frontend | AG-1 | 10000 | Epic | To Do | AG | agile7 | software | admin |  | Medium |  |  | admin | admin | 2020-01-24 20:52 | 2020-01-30 22:00 | 2020-01-30 12:41 |  |  |  | 0 |  | {quote}Craneware is the leader in automated value cycle solutions that improve financial performance for healthcare organizations. Cranewareâ€™s market-driven, SaaS solutions help hospitals and other healthcare providers more effectively price, charge, code and retain earned revenue for patient care services and supplies. *Application Vision*: The application should help patients around the US to compare prices of procedures across different hospitals, allowing them to reclaim the ability to find the most affordable care in their area *Customer Targets*: The prospect user is a person who needs medical treatment (either an Outpatient or Inpatient procedure) for an injury or a condition, and wants to compare prices from different institution. Their constraints are cost of the procedure and distance of the facility *Needs*: The needs we are trying to address with this product are: â€¢ability to find the cheapest price for a procedure/condition â€¢ability to restrict the search based on location (either live location or based on user input) â€¢ability to order results based either on price or distance â€¢ability to provide a list based on a custom ranking that is a combination of price, distance and user feedback. (Optional) â€¢ability to load new and edited data to update/add/delete from the existing data set (Optional) *Big Picture*: The user should be able to search for a procedure or a condition based on code or description, and the software should return a list of institution with an indication of the price and the distance as a primary output. The location can be derived used location data from a device or based on the user input. The list should be sortable by price or by distance. The secondary output should be the positioning of the information on a map, with price information showing on the placeholder. As a further requirement, it should be possible to restrict the search based on a price range or a distance range before running the search. *Product Features* â€¢Search based on code and procedure â€¢Add location information â€¢Match information based on code â€¢List display of matching information with details â€¢List sorting Map Integration Filtering â€¢ranking based on a combination of information (Nice to Have) â€¢machine learning based on user selection (Nice to Have) â€¢update data based on new/modified files loaded into the system (Nice to Have) â€¢Accessibility (Nice to Have){quote} Link to UI Design (incomplete) : [https://www.figma.com/file/lnHKf5EQHIyyxOmFfnpI8G/medicareSearch?node-id=2%3A73¦https://www.figma.com/file/lnHKf5EQHIyyxOmFfnpI8G/medicareSearch?node-id=2%3A73] |  | admin | [21 empty] | {} | ghx-label-13 |  | CW Frontend | To Do |  |  |  | 0¦hzzzzz:
Create a rest endpoint to update the existing data with a new csv file | AG-17 | 10016 | Story | To Do | AG | agile7 | software | admin |  | Low |  |  | admin | admin | 2020-01-26 20:14 | 2020-01-31 16:18 | 2020-01-31 13:48 |  |  |  | 0 | nice-to-have | h2. User Story As a developer I want to be able to update/ add/ delete data from the database via a rest endpoint h2. Conversation # Reprocessed CVS with coordinated provided with authentication # CSV as provided now with authentication # Update data with server restart h2. Acceptance Tests prove of create a *secured* rest endpoint tested that the database is updated h1. |  | admin | [12 empty] | AG-12 | [8 empty] | {} |  | AG-13 | [5 empty] | 0¦i00043:
Ability to add or modify existing data during runtime | AG-12 | 10011 | Story | To Do | AG | agile7 | software | admin |  | Low |  |  | admin | admin | 2020-01-25 18:09 | 2020-01-31 16:09 | 2020-01-31 11:59 |  |  |  | 0 | nice-to-have | h2. User story As the purchaser I want to be able to load new and edited data to update/add/delete from the existing data set. h2. Conversation Ability to enter new files to the database and use the provided rest endpoint functionality should be secured and only authorised user could perform this action to prevent malicious attacks. h2. Acceptance Tests Successful working user interface Ability to show that the database is updated Make sure it is connected to AG-17 |  | admin | [21 empty] | {} |  | AG-1 | [5 empty] | 0¦i0003w: |  |  |  |  | 5
User can input his location manually | AG-6 | 10005 | Story | To Do | AG | agile7 | software | admin |  | Low |  |  | admin | admin | 2020-01-24 21:34 | 2020-01-31 16:07 | 2020-01-31 12:46 |  |  |  | 0 | nice-to-have | h2. User story As a customer I want to be able to input my location manually into a text input. h2. Conversation Functionality is out of scope 2 options: a) click on the map where you would like to search (features an edit button) - 3-5 Story Points b) Search input with reverse geocoding service from google/mapbox integrated - 5 story points |  | admin | [21 empty] | {} |  | AG-1 | [5 empty] | 0¦i0004k:
Ask for user location | AG-4 | 10003 | Story | In Progress | AG | agile7 | software | admin |  | Low |  | admin | admin | admin | 2020-01-24 21:21 | 2020-01-31 16:28 | 2020-01-31 16:32 |  |  |  | 0 |  | h2. User Story As a customer I want the browser to ask for my location information, and then zoom and pan to the location/ coordinates on the map. h2. Conversation If the browser doesnâ€™t reveal the location, the map should stay the same as before or move to a default location. h2. Acceptance tests The browser zooms over to the userâ€™s location. This should happen in any location in the world, and can be tested by spoofing the browserâ€™s geolocation configuration. |  | admin | [21 empty] | {} |  | AG-1 | [5 empty] | 0¦i0000n: |  | AG Sprint 1 | AG Sprint 2 |  | 3
Provide a rank based on a combination of price/distance/ user feedback | AG-40 | 10039 | Story | To Do | AG | agile7 | software | admin |  | Lowest |  |  | admin | admin | 2020-01-31 12:05 | 2020-01-31 15:56 | 2020-01-31 12:41 |  |  |  | 0 |  | h2. User Story As a customer I want to be able to sort the results based on a combination of price, distance and user feedback. h2. Conversation Functionality is out of scope 2 Options: Rank only on combination of price and distance - 10 Story Points Rank with price, distance and feedback - 10 SP (original) + 10 SP (feedback) |  | admin | [21 empty] | {} | [7 empty] | 0¦i0004e:i